## Taskforce toolkit
Governance feedback tracker template
Use this template to track decisions and feedback from your governance bodies. An example is provided below but you should use and adapt the template to your Taskforce's needs.
Get started
Governance feedback tracker example
Committee | Date | Topic(s) | Comment |  | Responsible staff | How was feedback addressed? | Next steps
Secretaries Board | 2020-03-01 | Requested review and clearance of draft final report, before progression to Cabinet for final decision. | Committee directed revision of final recommendations to remove budget measures, which will be considered separately as part of the portfolio's broader budget submission. |  | Joe Smith | Budget measures (recommendations 3-5) removed. | Return to Secretaries Board on 1 May 2020 with updated draft. If cleared, final report will be considered by Federal Cabinet in June.

## Governance feedback tracker
Governance feedback tracker
Committee | Date | Topic(s) and actions | Comment and feedback | Responsible staff | How was feedback addressed? | Next steps
Name of Committee | Date of Committee meeting | What was the Committee asked to consider, and what actions were obtained from the Committee? | What significant discussion points and feedback arose from the meeting? | Which taskforce member(s) are responsible for actioning feedback? | Identify specific feedback, and actions taken to address that point. | E.g. Any comeback to the Committee?