## Slide 1: Agile policy playbook
How to use Agile methods and approaches to increase the effectiveness of your policy team
July 2020

## Slide 2: Overview
We’ve created this playbook to help you work more effectively as a team by using ‘Agile-inspired’ tools and techniques
Common challenges and lessons from the Policy Projects and Taskforce Office
Tips and templates for you to use with your team
Agile methodology ‘in a nutshell’
Key concepts and terms

## Slide 3: What is Agile?
Originating in software development, Agile is an iterative approach to problem solving and project management that empowers teams and can improve the quality and speed of delivery1,2.
A key benefit of the Agile methodology is the ability to apply some or all of its aspects to suit the needs and objectives of your team.
Core features and benefits of the methodology are summarised in the diagram.
Iterative approach
Goal-oriented planning
Team collaboration
Continuous learning
Concepts (rather than details) are used to seek feedback early and accelerate delivery and design
Goals and outcomes are used to focus and prioritise work
Increased transparency and team engagement empowers teams to solve problems together
Regular, structured reflection increases team effectiveness over time
Increased flexibility
Greater ‘customer’ satisfaction
Builds consensus with stakeholders
Greater team satisfaction
Teams think more broadly when developing solutions
Diversity of perspectives and skills used to solve problems leads to improved quality of output
Teams learn from their mistakes quickly and apply lessons learned
Features
&
Benefits2

## Slide 4: Key concepts and terms
What is scrum?
‘Scrum’ is one of the most popular Agile methods to tackle complex problems1. It comprises a series of meetings and roles2.
How it works
The work is divided into ‘sprints’ - a set duration (often a week) for goals and tasks to be achieved.
Team members commit to a series of meetings aimed to increase transparency, facilitate collaboration and encourage continuous improvement (see ‘Tips and Templates’ for more detail).
Certain roles can be assigned to provide direction and clarity, and these can be rotated amongst team members between sprints.
Tip: Watch this video for a 5 minute overview.
Key meetings
Roles and responsibilities
Delivery Team
Plans and delivers the work
Scrum Master
Facilitates meetings
Encourages active participation
Plays timekeeper role
Suited to a team member with prior exposure to Agile
Product Owner
In an APS environment, often an SES officer
Sets the direction and vision for a deliverable and provides quality assurance on final product
Sprint planning
Up to an hour
A recurring meeting scheduled at the beginning of each sprint to define the goals to be achieved during the sprint
Daily stand-up
15 minutes
A daily meeting for the team to agree on the tasks to be taken forward that day, assign responsibility and communicate any ‘blockers’
Sprint retro
Up to an hour
A recurring meeting at the end of each sprint to discuss what went well and what could be improved
Tip: The Scrum Master and Product Owner roles are not essential but can enhance team effectiveness.

## Slide 5: Common Scrum challenges and lessons from the PM&C Policy Projects and Taskforce Office
Challenge 1 – Lack of engagement by team members3
It takes a while to feel comfortable with the style and increased frequency of communication. Allow time for the team to gain confidence with the routine and practices of Scrum meetings.
Tips: Hold a meeting early to discuss how your team will use Agile ways of working to set clear expectations. Consider designating a ‘Scrum Master’ who will help ensure everyone participates in the discussion.
Challenge 2 – Poorly defined tasks can lead to inaccuracies and delays1
The aim of a Kanban (see box) is to break down work into chunks or items that can be completed in a day and increase transparency. But poorly defined tasks can create confusion and increase risk of duplication, and be a sign of imprecise goals.
Tips:
Take the time to nail your sprint goals.
Set realistic timeframes for each task (and if a task will take longer than a day, split it in two).
Ensure tasks are clear to everyone at stand-ups.
Keep the Kanban board up to date.
Challenge 4 – Lack of commitment to continuous improvement3
Agile practices emphasise the importance of continuous improvement, inherently acknowledging that things rarely go to plan. Committing to individual and team reflection helps teams become more effective and collaborative over time.
Tip: Hold sprint retros regularly to prompt ideas for continuous improvement and lessons learned.
Challenge 3 – Too much focus on day-to-day delivery makes you neglect the bigger picture
One of the strengths of Scrum is that it allows teams to work towards a solution even if the exact path is unclear at the start2. But it’s easy to get caught up in completing your day-to-day tasks and lose sight of the end goal.
Tip: Use your sprint planning meetings to ensure you remain on track.
To do
Doing
Done
Kanban board
The Scrum framework supports rapid product delivery (sprint planning and daily stand-ups) and helps teams regularly reflect on their performance (retros). However, the method can take a while for teams to get used to. Some strategies to manage common challenges include:
‘Kanban’ means ‘sign-board’ in Japanese. Toyota introduced the concept in the late 1940s when the company altered their manufacturing method. Vehicles were produced based on customer demand, rather than forecasting (i.e. new vehicles were manufactured only once complete ones were sold). This rule provides the basis for using Kanban boards outside of car manufacturing – the aim is to complete individual tasks before starting new ones to continue the ‘pull’ of work4.

## Slide 6: Tips and templates
Sprint planning, daily stand-ups and sprint retrospectives

## Slide 7: Sprint planning meetings
Purpose
  The sprint planning meeting is a recurring discussion for the team to come together and agree on a manageable number of sprint goals they’d like to achieve during the sprint (for example, ‘Submit decision brief to the PM’).
  The team should then sketch out the individual tasks required to achieve the sprint goals (which, for the example above, might include ‘Consult II&E on brief’ and ‘Clear brief through AS’).
WHO’S INVOLVED
Delivery team
WHEN TO USE IT
Start of sprint
Objectives
1
      Develop sprint goals
      Think about what needs to be done (refer to relevant planning material or sprint retro actions) and agree on sprint goals.
      Review items from product backlog
      Are there any items from the product backlog (list of tasks from previous sprints that haven’t been completed) that could be tackled in this sprint? Move them over into ‘To Do’ column.
2
      Agree on items / tasks for the sprint
      Put new tasks into the ‘To Do’ column.
      Each task should reflect a single activity or ‘step’ in a process to achieve each sprint goal. That way, tasks can be easily split across a number of team members and progress can be monitored at daily stand-up meetings.
3
Sprint Goal 1
Sprint Goal 2
Product backlog
Sprint retro actions
To do | Doing | Done
Task
Task
“What outcomes do we want to achieve?”
“What key milestones fall within this sprint?”
Key questions
      Kanban after sprint planning
Task
Task
Task
Task

## Slide 8: How to run a sprint planning session
      Before the session
Preparation
      Clear completed tasks (from ‘Done’ column on Scrum board).
2
      Schedule a meeting with the whole team (up to an hour should be sufficient).
3
1
      Review sprint retrospective outcomes (sprint retrospectives are discussed later in this document) and note any actions. Incorporate relevant actions into development of sprint goals (skip this step if its your first sprint planning session for the project).
      Nominate a ‘scrum master’ to plan and lead the discussion.
4
Agenda
Agree on a sprint duration that suits the workflow of your team. (E.g. weekly sprints for more rapid and iterative delivery, or fortnightly sprints if there is more time between deliverables).
A great starting point is the product backlog1 - a list of items that likely need to be completed but haven’t been allocated or prioritised yet.
If relevant, review your high-level plan or objectives to guide discussion of what the sprint goals should be (i.e. look at milestones and upcoming deadlines).
Focus on the outcomes – always link tasks back to the overarching sprint goals.
Be realistic – set goals that can be achieved in the sprint duration.
Tips and tricks
1
      Restate the overall objective for the project
      This is an important step to make sure you don’t lose sight of the bigger picture
2
      Discuss and agree your sprint goals for this sprint
      This is your chance to make sure everyone in your team understands your objective for the sprint
3
      Decide whether to move any tasks from the product backlog to the ‘to do’ column for this sprint
4
      Settle as a group on the individual tasks you will need to complete to achieve your sprint goals and add these to the ‘to do’ column

## Slide 9: Daily stand-ups
Purpose
  Team stand-ups are daily meetings for the delivery team to quickly clarify responsibility for individual tasks throughout a sprint.
WHO’S INVOLVED
Delivery team
WHEN WE USE IT
Daily (typically to start the day)
Objectives
1
      Clear tasks from ‘Doing’ to ‘Done’
      If this is not the first daily stand-up of the sprint, clear completed items from the day before from ‘Doing’ to ‘Done’.
      If team members need help with their items in ‘Doing’, daily stand-ups are a great opportunity to request or offer assistance.
      Self-assign tasks
      Team members select outstanding tasks from the ‘To do’ column and assign a due date (usually within the sprint). Mark initials on the task to clarify responsibility.
2
      If relevant to the current sprint, include additional tasks
      Try to avoid introducing major new tasks or ideas to the Kanban mid-sprint unless they are required to achieve your sprint goals.
3
To do | Doing | Done
Kanban board
Task
Task
Task
Task
Task
“Today I’m going to focus on the stakeholder engagement plan”.
“I’m still working on the project roadmap. I aim to circulate it this afternoon for feedback”.
“I’ll follow up with an email and suggest a time next week to discuss x”.

## Slide 10: How to run a daily stand up
      Before the session
Preparation
Plan the meeting around your team. The key is consistency – make it a daily team commitment (morning or afternoon).
Stand ups should be short and sharp and focused on who is doing what and how others can pitch in to help. We try to stick to 15 minutes and then let people get on with their work. Staying standing reduces the risk of rambling or loss of focus. If an issue requires further discussion, schedule a dedicated meeting.
Try to avoid introducing new ideas – that’s what sprint planning sessions are for.
The Kanban is great for capturing additional information to help your team work effectively together. Use the Kanban to capture useful reminders such as key dates, leave, extra-curricular commitments and other team learnings from sprint retros (e.g. ways of working, rules of engagement).
It can be helpful to divide the Kanban up into work streams to clarify responsibilities or priorities. For example, ‘stakeholder engagement’ and ‘research’ streams.
Tips and tricks
      Agree a time for a recurring daily meeting.
1
      Find a space to set up a Kanban board. Project management should be visual!
2
      Think about your day – what is achievable within the timeframe you have? What are the potential ‘blockers1’?
3
Your Kanban space could be a whiteboard, free wall space or online platform if working remotely (e.g. Microsoft Teams)
TIP

## Slide 11
Sprint retrospectives
Purpose
Sprint retrospectives are recurring meetings for the delivery team to come together and discuss what worked well and not so well at the end of a sprint. The structure of the meeting allows teams to reflect on collective and individual performance, and consider what can be improved in the future.
WHO’S INVOLVED
Delivery team
WHEN WE USE IT
End of sprint
Objectives
1
      Agree what went well
      As a group, identify any strengths and enablers of last sprint’s outcomes.
2
      Agree what didn’t go so well
      As a group, identify any weaknesses and blockers from the last sprint.
3
      Identify actions to take forward to improve team performance
      As a group, discuss lessons learned and identify practical actions to enable continuous improvement.

## Slide 12: How to run a sprint retrospective
      Ensure the team feels comfortable sharing views so honest opinions are aired (i.e. don’t make it personal, don’t take it personally. Listen with an open mind).
      There are many ways to run a retro. To encourage everyone to participate and reduce groupthink, we pause for two minutes after each guiding question (see next slide) and ask team members to reflect individually and write their ideas on individual Post-its. At the end of the two minutes, take turns to share your reflections and discuss with the group.
      Ensure the team spends adequate time evaluating both the product (outcome) and the process (how you got there).
      If your team needs help on agreeing next steps / actions, try asking team members to vote on which items should be prioritised.
      You may want to ask a neutral outsider to facilitate your retro.
Tips and tricks
      Before the retrospective
Preparation
      Find a meeting space for about 30 minutes to an hour.
1
      Nominate a facilitator.
2
      Prepare any supporting material (we generally use butchers paper, markers and Post-its; see right hand column for our process and the next slide for a template).
3
Agenda
1
      Set the scene
      Welcome everyone to the meeting and establish rules of engagement (see ‘Tips and tricks’).
      Evaluate sprint or project performance
      Start with the sprint goals – did we achieve them?
      Then discuss performance against goals using three guiding questions (see next slide).
2
      Wrap up and close
      Quickly run through list of actions, assign owners if relevant, and agree timeframes.
3

## Slide 13: Sprint retrospective template
Actions to take forward
  [Description.]
      Action 1
      Action 2
      Action 3
      Action 4
      Action 5
      Action 6
What worked well?
  [Description.]
What didn’t go so well?
  [Description.]
  [Description.]
How can we improve next time?
If working remotely there are a number of platforms, such as Miro, that can be used to run your sprint retro virtually.
TIP

## Slide 14: Continue your learning with these additional resources
Some examples of external information
Atlassian agile coach
Comprehensive and easy-to-digest guides on how to use agile in project delivery
Modern agile
Agile information, including links, resources and training activities
Articles
Embracing Agile, Harvard Business Review, 2016
Agile in Government, Deloitte Insights, 2017
How the public sector can remain agile beyond times of crisis, 2017
Agile as the next government revolution, BCG, 2018
Conquering the challenges of agile at scale in government, BCG, 2019
Scrum guide
Official scrum process guide