## Slide 1: Taskforce Administration Checklist Planning and Set-up (1 of 2)
Please note the following tasks and timeframes are indicative.
Before Commencement
Budget and finance
Determine budget (either through supplementary funding or from existing agency funding)
Establish a formal agreement on agency responsibilities for taskforce expenses
Establish financial management processes, including cost centre and cost codes
Decide who has financial delegations, and establish new delegations if necessary
Staff on-boarding
Organise security clearances
Issue staff request letters, highlighting staff attributes sought (external agencies) – consider brief interviews/trial period for staff
Issue MOU to secondees and their home agencies, setting out conditions of employment
Organise delegations for staff HR matters (e.g. timesheet and leave approvals)
Building access, IT and accommodation
Organise building passes for all staff
Organise work stations (including WHS and ergonomic adjustments) for all staff
Organise IT network access for all staff, including printer and photocopier access
Organise mobile technology (e.g. phones, laptops) for all staff
Organise car parking for SES officers
Organise document storage and disposal (e.g. appropriate filing cabinets and classified waste bins/shredders)
Day 1
Staff on-boarding
Designate a contact person for new starters, including meeting them on their first day
Ensure staff follow official agency induction processes – refer to host agency resources.
Ensure staff are briefed on agency policies, obligations and processes.
Ensure staff are aware of available facilities (kitchens, bathrooms, breakout areas, change rooms, bike storage, parking, lunch options).
Systems access
Ensure staff complete any prerequisite mandatory training for systems access (e.g. security and recordkeeping training)
Organise staff access to essential systems (e.g. HR and financial systems)
Organise staff access to executive briefing systems (e.g. PDMS, CabNet+)

## Slide 2: Taskforce Administration Checklist Planning and Set-up (2 of 2)
Please note the following tasks and timeframes are indicative.
Day 1 cont.
Records management
Establish a compliant records management system (e.g. existing team shared site/drive or establishing a new one)
Determine protocols for filing structure and file names
Determine protocols for Ministerial and executive submissions and correspondence (i.e. PDMS protocols)
Week 1
Information sharing and communication
Create and distribute list of staff contact details
Confirm standard words and titles to be used
Create taskforce inbox, and give taskforce staff access to the inbox
Create taskforce group distribution list
Create taskforce shared access arrangements on relevant systems (e.g. PDMS, CabNet+)
Notify host agency of taskforce existence and role (e.g. newsletter, presentation)
Staff management
Set up internal leave calendar
Set up performance management procedures and review processes for all staff
Other Set-up
Procurement
Before commencing, contact agency’s corporate services area to assist with the selection, gazettal process and developing the contract
Determine the process to be used to engage consultants (e.g. open source, select source, direct source or panel)
Determine the delegate with the authority to approve the procurement
Other administrative supports
Set up credit cards or travel cards (if required)
Establish taskforce templates (e.g. meeting agendas)
Ensure staff are provided the host agency’s privacy policies

## Slide 3: Taskforce Administration Checklist Closure and Handover (1 of 1)
Please note the following tasks are indicative.
Final Week
Terminate finance arrangements
Pay all outstanding invoices
Where costs will continue to accrue, advise nominated policy contact officer or the agency’s financial management area
Finalise records management
Ensure all records have been filed in accordance with the agency’s records management policies
Ensure all briefs and correspondence have been appropriately actioned and filed on the agency’s parliamentary workflow system
Close finished files or transfer active files to the relevant policy contact officer
Exit procedures
Advise the agency’s corporate services area of staff who will be leaving the agency for cessation of IT and building access and return of equipment. Refer staff to current agency exit processes.
Close taskforce shared access arrangements on relevant systems (e.g. PDMS, CabNet+)
Advise who will be the responsible area after the taskforce has finished, in the event of queries or follow-up (e.g. Senate Estimates).