## Project schedule
| Recruitment timeline | [5 empty] | Project start: | [7 empty] | 2026-05-25
| Role: | [Insert role title] |  |  |  |  | Display week: | [7 empty] | 1
| Classification: | [insert classification level] |  |  |  |  | Display week:
| TASK | ASSIGNED TO | CURRENT STATUS | START | END |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10
 | time axis 2026-05-18 to 2026-07-26
 | time axis 2026-05-18 to 2026-07-26
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Plan and Define
| Planning |  |  | 2026-05-25 | 2026-05-28 | 4 | bar: 2026-05-18 to 2026-05-21
| Delegate approval |  |  | 2026-05-29 | 2026-05-29 | 1 | bar: 2026-05-22
Attract
| Vacancy Advertised |  |  | 2026-06-01 | 2026-06-14 | 14 | bar: 2026-05-25 to 2026-05-29; 2026-06-01 to 2026-06-05
Select
| Shortlisting |  |  | 2026-06-15 | 2026-06-17 | 3 | bar: 2026-06-08 to 2026-06-10
| Assessments scheduled |  |  | 2026-06-18 | 2026-06-19 | 2 | bar: 2026-06-11 to 2026-06-12
| Interviews conducted |  |  | 2026-06-22 | 2026-06-24 | 3
| Work sample conducted |  |  | 2026-06-25 | 2026-06-26 | 2
| Referee checks |  |  | 2026-06-29 | 2026-07-01 | 3
| Selection report completed |  |  | 2026-07-02 | 2026-07-03 | 2
| Selection report approved |  |  | 2026-07-06 | 2026-07-06 | 1
Engage
| Verbal offers |  |  | 2026-07-07 | 2026-07-10 | 4
Formulas:
START = [END, row above]+1
END = [START]+1

## Plan and Define
Plan and Define
Planning your recruitment before advertising a role ensures all stakeholders, including hiring managers and panel members understand their role and the expected timeframes.
Step | Task | Responsibility | To commence | To be completed by
1 | Informal discussion with the delegate to seek in principle approval to fill vacancy
2 | Determine vacancy numbers to be filled. For example, is this a single vacancy or a bulk recruitment round?
3 | Decide if the vacancy needs to be filled on and ongoing or non-ongoing basis
4 | Will this process apply RecruitAbility? Will this process be run as an Affirmative Measure round?
5 | Undertake a role evaluation where necessary
6 | Identify the inherent requirements of the role
7 | Review and revise the role description/duty statement, ensuring it reflects the work-related qualities genuinely required to perform the role
8 | Complete the Recruitment planning overview, including information determined in the above steps
9 | Option 1: Fill vacancy via existing merit list or pool (proceed to seeking delegate approval). Go to step 22.
10 | Option 2: Advertise the vacancy on APSJobs
11 | Confirm panel members with appropriate diversity, experience and representation, including appropriate representation for affirmative measures processes.
12 | Confirm contact officer for advert (to be able to provide additional information about the role to potential candidates)
13 | Research and identify which selection activities (assessment methods) will identify the most suitable candidate/s aligned with the recruitment objectives and role requirements.
14 | Decide if a merit list or pool is intended to be established as the outcome, including the ideal size of the merit list or pool. This will depend on if there are potential similar vacancies that may arise, or if this is a bulk process
15 | Determine the suitable number of candidates that may progress through each stage of the assessment process. This will depend on the number of roles likely to be filled immediately and in the future. Tip - consider whether the process filling an individual vacancy or bulk round, and the ideal size of a merit list or pool if being established.
16 | Plan each stage of recruitment process and confirm panel member availability, for example: • what date will the job advertisement open / close • when will shortlisting be completed • when will interviews / other assessment tasks be conducted • what date will referee checks be done • when does the selection report need to be drafted and ready for delegate consideration and final approval
17 | Prepare candidate information by reviewing or creating the Candidate Information Kit Template for the vacancy
18 | Draft the job advertisement. Tip - is it clear, inclusive and compelling?
19 | Identify if there are appropriate additional advertising and sourcing channels to be used alongside APSJobs
20 | Develop contingency plans for common risks that may occur during recruitment processes i.e. panel member being away, technical difficulty when interviewing etc.
21 | Determine if a scribe will be used. If so, seek relevant delegate approval to commencement procurement
22 | Seek delegate approval to commence the recruitment activity, including approval for external services required i.e. scribes. For: • advertising vacancy on APSJobs continue on to Step 23 in Attract • accessing an established merit pool proceed to Step 32 in Select

## Attract
Attract
The attract phase commences once the recruitment process plan has been approved and ends once applications have closed. This stage should take approximately 2 working weeks.
Step | Task | Responsibility | To commence | To be completed by
23 | Publish the job ad on APSJobs and, if applicable, other approved platforms/ channels
24 | Monitor applications received
25 | Respond to candidate queries Tip - provide professional, prompt and positive responses to maintain candidate engagement
26 | Consider opportunities to provide further information to potential candidates
27 | Book meeting rooms as required, such as for • panel shortlist moderation • interviews and • any other proposed assessment tasks or panel discussions
28 | Send calendar invites to panel members to reserve time for shortlisting, panel shortlist moderation and placeholder interview times
29 | If a scribe is being used, send calendar invites for assessment items and any other key dates. Tip - Also provide any other any relevant templates (i.e. selection report) to support an efficient process
30 | Finalise the assessment methods, including interview/work sample assessment questions
31 | HR / Recruitment Team to brief panel members on their roles and responsibilities. Including, but not limited to: • the work-related qualities that are being assessed • how to ensure the process upholds the merit principles • requirement to notify the delegate and HR / Recruitment of any perceived or actual conflicts of interest • information of unconscious bias • what to do if they are unavailable at any point throughout the recruitment process.

## Select
Select
The select phase commences once applications have closed and ends, once all candidates have been notified of the selection process outcome. Selection activities should be completed where possible within 3 working weeks. The following provides some targets as a guide: • 5 working days for shortlisting and notify candidates of next assessment activity (i.e. interview) • 5 - 8 working days to conduct assessments, including referee reports • 3 - 5 working days to finalise selection report and receive delegate approval
Step | Task | Responsibility | To commence | To be completed by
32 | If using an existing merit list or pool: Request access to the merit pool from the owning agency. If the request is approved by the owning agency, before considering candidates, proceed with: • Steps 35, 36, 37 & 38 Then proceed with consideration of candidates on list, then proceed to: • Step 49 if referee checks are required (recommended if the merit pool is more than 6 months old) and then • Step 54 to seek delegate approval
33 | Confirm that applications have closed and all submissions are captured
Conflict of Interest declarations
34 | List of candidate names provided to panel members and delegate to check for any conflicts of interest
35 | Panel members to complete and return Conflict of Interest (CoI) Declaration
36 | Where CoIs are identified, discuss with the delegate and decide on mitigation strategies. If mitigation strategies are not viable, panel members may need to be replaced
37 | Check if any panel members have been listed as referees by candidates. Seek written referee reports from panel members who are listed as referees
Shortlisting
38 | Recruitment/ HR Team to provide panel members with applications for shortlisting - only after CoIs declared and mitigation strategies decided, and any referee reports completed by panel members.
39 | Panel to independently assess all applications against the agreed work-related qualities to create a shortlist
40 | Panel undertakes moderation of shortlisting to ensure panel is aligned on shortlist
41 | Panel to ensure shortlist decision is documented for inclusion in the Selection Report
42 | HR team to review candidates' integrity related question responses and determine if investigation / further information is required | HR Team
43 | Where required, HR Team to engage with delegate on integrity questions and proposed approach to further investigations / requirement to seek further information
44 | Where required, undertake further investigation or seek further information on integrity check responses (for shortlisted candidates who responded 'yes' and deemed appropriate to seek further information) | HR Team
45 | Notify candidates of shortlist outcome, including providing information of the panel members and the format of the assessment process (e.g. interviews or other assessment methods that will be used).
46 | For shortlisted candidates - provide invitation to interview, including offer of reasonable personalised adjustments
47 | Share completed interview schedule with the panel (and scribe if using)
Assessment
48 | Conduct interviews, and any other assessments, including: • recording detailed notes • preliminary ratings for each candidate and • utilise the Assessment rubrics tool. Panels will usually undertake comparative assessments of candidates as they progress through and at the conclusion of the assessment/s (i.e. interviews).
49 | Seek referee reports for candidates rated suitable after interview and / or other assessments | Panel chair
50 | Where any adverse referee comments are received, the panel should discuss with their HR team for guidance on how to proceed. Procedural fairness requires that the candidate be given a reasonable opportunity to respond. See Factsheet: Referee checks for further information
51 | Panel to meet to review referee reports and comparatively assess all candidates based on their performance throughout the recruitment process
Selection
52 | Utilise the Selection Report template, including information on: • individual candidate assessments, including comments on each assessment item, if the candidate is suitable and to be placed in a merit list or pool; and • if/how the candidate demonstrated the work-related qualities required for the role; and • a summary of referee comments received | Scribe or Panel Chair
53 | Send selection report to panel members for review and agreement
54 | Send selections report to delegate for consideration and approval
55 | Notify all candidates of outcome and provide opportunity for feedback
56 | Respond to any requests for feedback Tip - provide timely and constructive respones to maintain agency reputation
57 | If using an established merit pool - seek delegate approval to engage identified candidate

## Engage
Engage (until verbal offer as written offer requires security clearance)
The engage phase begins after assessments are complete and candidates are selected. It is time to prepare information to contact the successful candidate and assist them to have a smooth onboarding process. This stage should take approximately 1 working week.
Step | Task | Responsibility | To commence | To be completed by
58 | Provide verbal offer to successful candidate/s
59 | Undertake pre-employment integrity checks
60 | Commence onboarding preparation – provide confirmation on next steps to successful candidate/s i.e. security clearance

## Resources
Resources
Phase | Document
Plan and Define | The APS merit principle
Recruitment in the APS Guide
Creating and sharing merit lists or pools
Factsheet: Advertising a location for a vacancy
APSC Recruitment factsheets
Candidate Information Kit Template*
Recruitment Planning Overview Template*
Attract | Public Service Gazette requirements
Select | APS Conflict of Interest Management Framework: Better Practice Model
Factsheet: Managing conflict of interest in recruitment
Factsheet: Referee checks
Selection Report Template*
Factsheet: Creating effective merit lists*
Engage
* Future resources currently under development